## Definitions
Measurements |  |  |  | Metrics
ID | Measurement | Description | Significance | ID | Metric | Associated Measurements | Significance
1 | # of bugs | The total current number of bugs recorded and active | Provides some indication of application quality and progression | 1 | # bugs/SLOC (source lines of code) | 1,2 | Provides an indication of quality assuming bugs are kept up to date, and assuming some issue determining bug causality and interdependency. Tracking number of bugs per SLOC may help determine which areas of code are more complicated and bug-prone. The team may then focus more on ensuring any logic or other code in those sections are correct.
2 | SLOC (source lines of code) | Excludes comments and whitespace in code. | Provides a measurement of meaningful lines of code written | 2 | % program statements called during execution of the entire test suite (statement coverage) | 2,6,7 | Computing how much code our test suite covers helps us determine how comprehensive our test suite is. This in turn helps determine which areas of the code need more test coverage, in order to discover and prevent bugs in the future.
3 | # total commits | The number of commits to our team repository | Provides some indication of application development speed | 3 | # of commits per week | 3 | Provides an indication of development speed. This will likely start low, speed up and remain consistent for a while (for the most part), and then drop some towards the end of the project. Any significant dips or peaks mid-project need to be evaluated in order to ensure team members are contributing enough towards the project.
4 | # total risks | The number of risks documented in the team risk spreadsheet | Tracks how many risks our team has discovered and evaluated | 4 | # risks added per week | 4 | Calculating risks added per week helps determine the stability of the project. If risks keep getting added, either the project is becoming increasingly unstable or the team is retroactively adding risks that should have been thought of and addressed in the beginning of the project. Both cases somewhat jeopardize the project.
5 | # total inactive risks | The number of inactive risks documented in the team risk spreadsheet | Tracks how many risks our team has overcome such that they are no longer relevant to the project | 5 | % relevant risks= ((# total risks - # inactive risks)/# total risks) | 4,5 | The percentage relevant risks helps the team determine how the project is progressing. If more risks become relevant over time, it may indicate some stability or issues arising. The percentage relevant risks should eventually trend downward as the project progresses and risk become inactive/no longer relevant.
6 | # of tests | The number of tests currently in the team repository | Tracks the number of tests our team has created, indicating test suite size | 6
7 | # statements called in test suite | The number of statements called during execution of all tests in the team repository | Provides an indication of test coverage | 7
8 |  |  |  | 8
9 |  |  |  | 9
10 |  |  |  | 10
11 |  |  |  | 11
12 |  |  |  | 12
13 |  |  |  | 13

## Measurements
Week | # of (closed) bugs | # of (open) bugs | SLOC (source lines of code) | # total commits | # total risks | # total inactive risks | # of tests | # statements called in test suite | requirements added
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://github.com/flosse/sloc
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 16 | 1 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 16 | 1 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 18 | 1 | 0 | 0 | 0
6 | 0 | 0 | 0 | 3 | 20 | 1 | 0 | 0 | 0
7 | 0 | 0 | 0 | 18 | 20 | 1 | 0 | 0 | 0
8 | 0 | 0 | 0 | 23 | 25 | 1 | 45 | 0 | 0
9 | 0 | 0 | 0 | 24 | 25 | 1 | 45 | 0 | 0
10 | 0 | 0 | 0 | 24 | 26 | 1 | 0 | 0 | 0 | - iteration 3, dev starts
11 | 0 | 0 | 0 | 24 | 26 | 1 | 0 | 0 | 0
12 | 0 | 5 | 2329 | 53 | 26 | 1 | 0 | 0 | 14
13 | 0 | 5 | 2433 | 62 | 26 | 1 | 0 | 0 | 0
14 | 0 | 5 | 2693 | 87 | 26 | 1 | 0 | 0 | 0
15 | 6 | 5 | 2754 | 109 | 26 | 1 | 6 | 155/496 | 1 | ios m\ap stuff added, tests written & test coverage started to be tracked
16 | 3 | 5 | 10076 | 120 | 26 | 1 | 6 | 155/496 | 0
finals | 0 | 3 | 10076 | 120 | 26 | 1 | 6 | 155/496 | 0
winter break | 0 | 3 | 10109 | 123 | 26 | 1 | 6 | 155/496 | 0
1 | 0 | 3 | 10109 | 123 | 26 | 1 | 6 | 155/496 | 0
2 | 0 | 6 | 10270 | 125 | 26 | 1 | 6 | 155/496 | 0
3 | 2 | 6 | 10270 | 148 | 27 | 5 | 6 | 155/496 | 0
4 | 5 | 5 | 10328 | 166 | 27 | 5 | 6 | 155/496 | 0
5 | 0 | 8 | 10473 | 207 | 27 | 5 | 6 | 155/496 | 0
6 | 0 | 8 | 3753 | 211 | 27 | 5 | 6 | 155/496 | 0 | some html docs were removed -> lower loc count
7 | 0 | 11 | 3850 | 212 | 27 | 5 | 6 | 155/497 | 0
8 | 1 | 12 | 3898 | 241 | 27 | 5 | 6 | 155/498 | 0
9 | 0 | 12 | 3944 | 258 | 27 | 5 | 6 | 155/499 | 0
10 | 0 | 12 | 4089 | 307 | 27 | 11 | 6 | 155/500 | 0
11
12
13
14

## Metrics
Week | # bugs/KLOC | # bugs/SLOC (source lines of code) | % program statements called during execution of the entire test suite (statement coverage) | # of commits per week | # risks added per week | % relevant risks= ((# total risks - # inactive risks)/# total risks)*100
1 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 16 | 93.75
4 | 0 | 0 | 0 | 0 | 0 | 93.75
5 | 0 | 0 | 0 | 0 | 2 | 94.44444444
6 | 0 | 0 | 0 | 3 | 2 | 95
7 | 0 | 0 | 0 | 15 | 0 | 95
8 | 0 | 0 | 0 | 5 | 5 | 96
9 | 0 | 0 | 0 | 1 | 0 | 96
10 | 0 | 0 | 0 | 0 | 1 | 96.15384615 | - iteration 3, started dev
11 | 0 | 0 | 0 | 0 | 0 | 96.15384615
12 | 2.146844139 | 0.002146844139 | 0 | 29 | 0 | 96.15384615
13 | 2.055076038 | 0.002146844139 | 0 | 9 | 0 | 96.15384615
14 | 1.856665429 | 0.001856665429 | 0 | 25 | 0 | 96.15384615
15 | 1.815541031 | 0.001815541031 | 31.25% (155/496) | 22 | 0 | 96.15384615 |  | ios m\ap stuff added, tests written & test coverage started to be tracked
16 | 0.4962286622 | 0.0004962286622 | 155/496 | 11 | 0 | 96.15384615
finals | 0.2977371973 | 0.0002977371973 | 155/496 | 0 | 0 | 96.15384615 |  | at end of semester, consider doing a graph/metric on estimation accuracy too (for time worked actual vs estimated)
winter break | 0.2967652587 | 0.0002967652587 | 155/496 | 3 | 0 | 96.15384615
1 | 0.2967652587 | 0.0002967652587 | 155/496 | 0 | 0 | 96.15384615
2 | 0.5842259007 | 0.0005842259007 | 155/496 | 2 | 0 | 96.15384615
3 | 0.5842259007 | 0.0005842259007 | 155/496 | 23 | 1 | 81.48148148
4 | 0.4841208366 | 0.0004841208366 | 155/496 | 18 | 0 | 81.48148148
5 | 0.7638689965 | 0.0007638689965 | 155/496 | 41 | 0 | 81.48148148
6 | 2.131628031 | 0.002131628031 | 155/496 | 4 | 0 | 81.48148148
7 | 2.857142857 | 0.002857142857 | 155/497 | 1 | 0 | 81.48148148
8 | 3.078501796 | 0.003078501796 | 155/498 | 29 | 0 | 81.48148148
9 | 3.042596349 | 0.003042596349 | 155/499 | 17 | 0 | 81.48148148
10 | 2.934702861 | 0.002934702861 | 155/500 | 49 | 0 | 59.25925926
11 | #DIV/0! | #DIV/0! |  | -307 | -27 | #DIV/0!
12 | #DIV/0! | #DIV/0! |  | 0 | 0 | #DIV/0!
13 | #DIV/0! | #DIV/0! |  | 0 | 0 | #DIV/0!
14 | #DIV/0! | #DIV/0! |  | 0 | 0 | #DIV/0!

## Entire Proj Graphs
below graph is only first semester and first couple weeks of this one, since timekeeping isnt up to date